## RND Counsel_Updated Version
DEFECT TRACKING LOG FOR HRMS - ICC Evaluation Form Application
S.No | Defect ID | Created Date | Created By | Defect Description | Module Name | Sub Module Name | User View | Assigne To | Severity | Priority | Status | Resoultion | Resolution Date | Comments
1 | HRMS_ICC_EF_01 | 2018-10-01 | Kanakarajan Kandasamy | Venu filed is allowing to enter only numbers. The field is allowing to enter Alphabets (Conference Hall) and Alpahanumerical Field (Bio Lab 3). | Add Traning Entry |  | HR Admin | Lavanya BR | Major | Medium | New
2 | HRMS_ICC_EF_02 | 2018-10-01 | Kanakarajan Kandasamy | A proper warning message is not displaying for invalid date formate entry. ( Steps :-Traning Entry -> Enter all the ncessary details (in date field enter the date like 123445566778) ) -> Click Submit | Add Traning Entry |  | HR Admin | Lavanya BR | Major | Medium | New
3 | HRMS_ICC_EF_03 | 2018-10-01 | Kanakarajan Kandasamy | Save Sucessfully dispaying in another screen. (Traning Entry - >Enter all the ncessary details - Click Submit ) | Add Traning Entry |  | HR Admin | Lavanya BR | Major | High | New
4 | HRMS_ICC_EF_04 | 2018-10-01 | Kanakarajan Kandasamy | There is a difference between HRMS employee count (251) and ICC Traning Report total employee count (243). (Steps:- Traning Entry -> Enter all the necessary details (in date field enter the date like 123445566778) ) -> Click Submit -> Click View Report like displaying in the Traning Entry Grid -> Check it out Total Employee Column) | Add Traning Entry | ICC Traning Report | HR Admin | Lavanya BR | Major | High | New
5 | HRMS_ICC_EF_05 | 2018-10-01 | Kanakarajan Kandasamy | We have not entered any time in "Enter the Training Program Details Form", but the Time is displaying along with the date.(Steps:- Traning Entry -> Enter all the necessary details (in date field enter the date like 123445566778) ) -> Click Submit -> Click View Report like displaying in the Traning Entry Grid -> Check it out Date field ) | Add Traning Entry | ICC Traning Report | HR Admin | Lavanya BR | Major | High | New
6 | HRMS_ICC_EF_06 | 2018-10-01 | Kanakarajan Kandasamy | The date field is allowing to select the greater than and less than the current date. (Steps :- Login -> -> Click on the Feedback Link-> Select the Date ) | Employee Feedback |  | ICC User | Lavanya BR | Major | High | New
7 | HRMS_ICC_EF_07 | 2018-10-01 | Kanakarajan Kandasamy | This is not a defect. If we load Title and Location of training details and Trainer details from the " Enter the Training Program Details "' form means we may avoid confusion. (Steps :- Login -> -> Click on the Feedback Link-> Check it out the respective fields.) | Employee Feedback |  | ICC User | Lavanya BR | Major | High | New