## RND Counsel_Updated Version
DEFECT TRACKING LOG FOR HRMS - ICC Evaluation Form Application
S.No | Defect ID | Created Date | Created By | Defect Description | Module Name | Sub Module Name | User View | Assigne To | Severity | Priority | Status | Resoultion | Resolution Date | Comments
1 | HRMS_ICC_EF_01 | 2018-10-01 | Kanakarajan Kandasamy | Venu filed is allowing to enter only numbers. The field is allowing to enter Alphabets (Conference Hall) and Alpahanumerical Field (Bio Lab 3). | Add Traning Entry |  | HR Admin | Lavanya BR | Major | Medium | Reopen | It is not Compulsory to Enter both alphanumeric , So it Occurs Problem if the validation is Done . | 2018-01-10 | Please Fix this defect I confirm same with Mr.Rajesh
2 | HRMS_ICC_EF_02 | 2018-10-01 | Kanakarajan Kandasamy | A proper warning message is not displaying for invalid date formate entry. ( Steps :-Traning Entry -> Enter all the ncessary details (in date field enter the date like 123445566778) ) -> Click Submit | Add Traning Entry |  | HR Admin | Lavanya BR | Major | Medium | Reopen | Issue Fixed | 2018-01-10 | Defect Fixed but still, the field is allowing to enter numbers. Suppose if the user has not selected any date means that the field is taking current data as default date.
3 | HRMS_ICC_EF_03 | 2018-10-01 | Kanakarajan Kandasamy | Save Sucessfully dispaying in another screen. (Traning Entry - >Enter all the ncessary details - Click Submit ) | Add Traning Entry |  | HR Admin | Lavanya BR | Major | High | Closed | Alert Message varies based on Browser . | 2018-01-10 | NA
4 | HRMS_ICC_EF_04 | 2018-10-01 | Kanakarajan Kandasamy | There is a difference between HRMS employee count (251) and ICC Traning Report total employee count (243). (Steps:- Traning Entry -> Enter all the necessary details (in date field enter the date like 123445566778) ) -> Click Submit -> Click View Report like displaying in the Traning Entry Grid -> Check it out Total Employee Column) | Add Traning Entry | ICC Traning Report | HR Admin | Lavanya BR | Major | High | Closed | Irrespective of Managers , Only Employee Count is shown . | 2018-01-10 | NA
5 | HRMS_ICC_EF_05 | 2018-10-01 | Kanakarajan Kandasamy | We have not entered any time in "Enter the Training Program Details Form", but the Time is displaying along with the date.(Steps:- Traning Entry -> Enter all the necessary details (in date field enter the date like 123445566778) ) -> Click Submit -> Click View Report like displaying in the Traning Entry Grid -> Check it out Date field ) | Add Traning Entry | ICC Traning Report | HR Admin | Lavanya BR | Major | High | Closed | Issue fixed | 2018-01-10 | Defect Fixed and woring fine now
6 | HRMS_ICC_EF_06 | 2018-10-01 | Kanakarajan Kandasamy | The date field is allowing to select the greater than and less than the current date. (Steps :- Login -> -> Click on the Feedback Link-> Select the Date ) | Employee Feedback |  | ICC User | Lavanya BR | Major | High | Fixed | Issue Fixed | 2018-01-10
7 | HRMS_ICC_EF_07 | 2018-10-01 | Kanakarajan Kandasamy | This is not a defect. If we load Title and Location of training details and Trainer details from the " Enter the Training Program Details "' form means we may avoid confusion. (Steps :- Login -> -> Click on the Feedback Link-> Check it out the respective fields.) | Employee Feedback |  | ICC User | Lavanya BR | Major | High | Fixed | Issue Fixed | 2018-01-10
8 | HRMS_ICC_EF_08 | 2018-11-01 | Kanakarajan Kandasamy | Time is displaying along with the traning program created date. (Login :- Self Servise -> Training Evaluation -> Check it out the Date column displaying In Traning Program Details page) | Self Servise | Training Evaluation | ICC User |  | Minor | Medium | New
9 | HRMS_ICC_EF_09 | 2018-11-01 | Kanakarajan Kandasamy | Feedback Button Problem. (Steps : - > Login -> -> Click on the Feedback Link (Ex- SP4)-> Fill all the necessary details in Tranining Evaluation Form -> Click Save -> Click Back -> Now check SP15 row feedback) | Employee Feedback |  | ICC User | Lavanya BR | Major | High | New
10 | HRMS_ICC_EF_10 | 2018-11-01 | Kanakarajan Kandasamy | Date displaying in the Evaluation Form is not displaying in the feedback completed report. (Steps:- Login -> click on the View Report link displaying in the " Enter the Traning program details " page grid -> Drill down the Feedback Completed count displaying in the ICC Report Page -> Click on the View Report displaying in the ICC Feedback Completed Report page.) | Employee Feedback | ICC Training Report | HR Admin | Lavanya BR | Major | High | New